## Requests
Request_ID | Request_Type | Date_Received | Requester | Action_Required | Description | Priority | Deadline | Target_Completion | Owner | Status
REQ-001 | Documentation Update Request | 2026-10-16 09:15 | Laura Méndez | To coordinate the process of updating employee safety documentation in the database. | Laura from Human Resources requests to update safety documentation from an unknown employee. Employee's identification will be provided then. | Medium | 2026-10-23 | 2026-10-21 | Administrative Support | Waiting
REQ-002 | Meeting Coordination | 2026-10-19 08:42 | Michael Torres | To coordinate and book a meeting between Operations and Finance team | Michael Torres, the Operations Manager requests a meeting between Operations team and Financial team to discuss PRJ-004's administrative requirements. | High | 2026-10-21 | 2026-10-19 | Administrative Support | In Progress
REQ-003 | Invoice Check | 2026-10-19 08:50 | Sarah Collins | To check invoice information, matching details of the purchase information | Sarah Collins requests administrative support to check invoice information by matching purchase details | High | 2026-10-20 | 2026-10-19 | Administrative Support | Waiting

## Tasks
Task_ID | Request_ID | Task_Description | Owner | Due_Date | Status
TSK-001 | REQ-001 | Request missing employee identification and deadline from Laura Méndez. | Administrative Support | 2026-10-19 | Done
TSK-002 | REQ-002 | Checking meeting availability with Finance and operations team | Administrative Support | 2026-10-19 | Done
TSK-003 | REQ-003 | Checking Invoice information and matching it with purchase details, to confirm invoice | Administrative Support | 2026-10-20 | Done
TSK-004 | REQ-002 | To coordinate participants from Operations and Finance with Operation Manager | Administrative Support | 2026-10-19 | Done
TSK-005 | REQ-002 | To book meeting between Operations Manager, Operations and Finance team | Administrative Support | 2026-10-19 | Done
TSK-006 | REQ-002 | To send meeting invitation to participants | Administrative Support | 2026-10-19 | Done
TSK-007 | REQ-003 | Retrieving PO-017 from ERP system | Administrative Support | 2026-10-19 | Done
TSK-008 | REQ-003 | To inform to Sarah Collins or Fiannce team a inconsistency was identified | Administrative Support | 2026-10-19 | Done

## Activity_Log
Activity_ID | Resquest_ID | Activity_Date | Activity_Type | Performed_By | Description
ACT-001 | REQ-001 | 2026-10-16 09:45 | Information Request | Administrative Support | Sent a simulated email to Laura Méndez requesting the employee's full name, ID, department, and documentation update deadline.
ACT-002 | REQ-002 | 2026-10-19 09:00 | Meeting coordination | Administrative Support | Sent a simulated email to Finance and Operations teams checking availability to a meeting with Operation manager to review administrative requirements
ACT-003 | REQ-002 | 2026-10-19 10:00 | Parcticipants coordination | Administrative Support | Sent a simulated email to Operations Team to coordinate the meeting with Operation Manager and Finance
ACT-004 | REQ-002 | 2026-10-19 10:30 | Meeting arrangement | Administrative Support | Set a simulated meeting for Operations Manager, Finance and Operations team.
ACT-005 | REQ-002 | 2026-10-19 10:45 | Meeting invitation | Administrative Support | Sent a simulated email containing meeting link and aditional information
ACT-006 | REQ-003 | 2026-10-19 11:00 | Retrieving PO-017 document | Administrative Support | Retrieved a simulated purchase order documento to be compare with Invoice INV-017
ACT-007 | REQ-003 | 2026-10-19 11:10 | Matching PO-017 and INV-017 | Administrative Support | Compared INV-017 against PO-017. Identified a USD 50 discrepancy in the Ground Leveler unit price ($650 invoiced vs. $600 ordered). All other listed items, quantities, and prices matched.
ACT-008 | REQ-003 | 2026-10-19 11:20 | Informing PO-017 and INV-017 Discrepancy | Administrative Support | Sent a simulated email to Sarah Collins reporting a USD 50 discrepancy between INV-017 and PO-017 and requesting confirmation of the price difference.